## Sheet1
TABLE MATRIX
ACTIVITY | INTIAL (ORIGIN) | FINAL (DESTINATION) | DURATION (1)
A = PRELIM | 1 | 2 | 1 WEEK & 3 DAYS
B = ANALYSIS | 2 | 3 | 1 WEEK & 2 DAYS
C = DESIGN | 3 | 4 | 10 WEEKS
D = DEVELOPMENT | 4 | 5 | 18 WEEKS
E = IMPLEMENTATION | 5 | 6 | 5 WEEKS
F = EVALUATION | 6 | 3 | 4 WEEKS
GANTT CAHRT (WATERFALL MODEL)
DELIVERABLES | NUMBER OF WEEKS = 18 WEEKS
A. PRELIMINARY
B. ANALYSIS
C. DESIGN
D. DEVELOPMENT
E. IMPLEMENTATION
F. EVALUATION